## Sheet1
Task ID | Task Description | Status | Type | Start Version | Last Changed Version
1 | Design Document | In process | Doc | 1.0 | 1.0
1.1 | Customizing Document | Complete | Doc | 1.0 | 1.0
1.2 | Customizing Default value | In process | Doc | 1.0 | 1.0
1.3 | UI Layout Design | In process | Doc | 1.0 | 1.0
2 | Android Development | Not Start | Dev | 1.0 | 1.0
2.1 | Establish the android project | Complete | Dev | 1.0 | 1.0
2.2 | Backend development(com.jasonzqshen.familyFinance.core) | In process | Dev | 1.0 | 1.0
2.2.1 | CoreDriver development(com.jasonzqshen.familyaccounting.core.CoreDriver). And it follows the singleton pattern. | In process | Dev | 1.0 | 1.0
2.2.1 | Master data development(com.jasonzqshen.familyFinance.core.masterdata) | Not Start | Dev | 1.0 | 1.0
2.2.1.1 | Master data base class development | In process | Dev | 1.0 | 1.0
2.2.1.1.1 | Base funtion(constructor, variable, id, description) | Complete | Dev | 1.0 | 1.0
2.2.1.1.2 | To XML | Not Start | Dev | 1.0 | 1.0
2.2.1.3 | Master data identity | Complete | Dev | 1.0 | 1.0
2.2.1.2 | G/L account master data development | Not Start | Dev | 1.0 | 1.0
2.3 |  |  |  | 1.0 | 1.0
3 | Unit Test | Not Start | Test | 1.0 | 1.0
3.1 | Core Test Case | In process | Test | 1.0 | 1.0
3.1.1 | Master Data Test Case | Complete | Test | 1.0 | 1.0
3.1.2 | Transaction Data Test Case | In process | Test | 1.0 | 1.0
3.2 | Core test data | In process | Test | 1.0 | 1.0
3.2.1 | Master Data Test Data | In process | Test | 1.0 | 1.0
3.2.2 | Transaction Data Test Data | In process | Test | 1.0 | 1.0