## Sheet1
Task ID | Task Description | Status | Type | Start Version | Last Changed Version | In process
1 | Design Document | In process | Doc | 1.0 | 1.0 | Complete
1.1 | Customizing Document | Complete | Doc | 1.0 | 1.0 | Not Start
1.2 | Customizing Default value | Complete | Doc | 1.0 | 1.0
1.3 | UI Layout Design | In process | Doc | 1.0 | 1.0
1.3.1 | Entry view design
2 | Android Development | Not Start | Dev | 1.0 | 1.0
2.1 | Android UI Development | In process | Dev | 1.0 | 1.0
2.1.1 | Entry view development | Not Start
2.2 | Backend development(com.jasonzqshen.familyFinance.core) | In process | Dev | 1.0 | 1.0
2.2.1 | CoreDriver development(com.jasonzqshen.familyaccounting.core.CoreDriver). And it follows the singleton pattern. | In process | Dev | 1.0 | 1.0
2.2.2 | Master data development(com.jasonzqshen.familyFinance.core.masterdata) | Complete | Dev | 1.0 | 1.0
2.2.2.1 | Master data base class development | Complete | Dev | 1.0 | 1.0
2.2.2.1.1 | Base funtion(constructor, variable, id, description) | Complete | Dev | 1.0 | 1.0
2.2.2.1.2 | To XML | Complete | Dev | 1.0 | 1.0
2.2.2.1 | Master data identity | Complete | Dev | 1.0 | 1.0
2.2.2.2 | G/L account master data development | Complete | Dev | 1.0 | 1.0
2.2.2.3 | G/L account Group master data development | Complete | Dev | 1.0 | 1.0
2.2.2.4 | Vendor master data development | Complete | Dev | 1.0 | 1.0
2.2.2.5 | Customer master data development | Complete | Dev | 1.0 | 1.0
2.2.2.6 | Bank Key master data development | Complete | Dev | 1.0 | 1.0
2.2.2.7 | Bank Account master data development | Complete | Dev | 1.0 | 1.0
2.2.2.7 | Business Area master data development | Complete | Dev | 1.0 | 1.0
2.2.3 | Transaction data(Head Entity & Item Entity) | Complete | Dev | 1.0 | 1.0
2.2.3.1 | Load | Complete | Dev | 1.0 | 1.0
2.2.3.2 | Store | Complete | Dev | 1.0 | 1.0
2.2.3.3 | General Entry | Complete | Dev | 1.0 | 1.0
2.2.3.4 | Customer invoice entry | Complete | Dev | 1.0 | 1.0
2.2.3.5 | Vendor invoice entry | Complete | Dev | 1.0 | 1.0
2.2.3.6 | G/L entry | Not Start | Dev | 1.0 | 1.0
2.2.4 | Entry data customizing | Not Start | Dev | 1.0 | 1.0
2.2.5 | Reverse | Complete | Dev | 1.0 | 1.0
2.2.6 | Report | In process | Dev | 1.0 | 1.0
2.2.6.1 | G/L account balance report | Complete | Dev | 1.0 | 1.0
3 | Unit Test | In process | Test | 1.0 | 1.0
3.1 | Core Test Case | In process | Test | 1.0 | 1.0
3.1.1 | Master Data Test Case | Complete | Test | 1.0 | 1.0
3.1.1.1 | Master Data Test Case - load | Complete | Test | 1.0 | 1.0
3.1.1.2 | Master Data Test Case - create/remove entity | Complete | Test | 1.0 | 1.0
3.1.1.2 | Master Data Test Case - store | Complete | Test | 1.0 | 1.0
3.1.2 | Transaction Data Test Case | Complete | Test | 1.0 | 1.0
3.1.2.1 | Transaction Data Test Case - load | Complete | Test | 1.0 | 1.0
3.1.2.2 | Transaction Data Test Case - store | Complete | Test | 1.0 | 1.0
3.1.2.3 | Transaction Data Test Case - customer invoice entry | Complete | Test | 1.0 | 1.0
3.1.2.4 | Transaction Data Test Case - vendor invoice entry | Complete | Test | 1.0 | 1.0
3.1.2.5 | Transaction Data Test Case - g/l entry | Complete | Test | 1.0 | 1.0
3.1.2 | Transaction Data Test Case | In process | Test | 1.0 | 1.0
3.2 | Report test data | In process | Test | 1.0 | 1.0
3.1.2.1 | G/L account balance report data | Complete | Test | 1.0 | 1.0
3.2.1 | Master Data Test Data | Complete | Test | 1.0 | 1.0
3.2.2 | Transaction Data Test Data | Complete | Test | 1.0 | 1.0